DocuEnv — Development Plan

Project 3 | Version 1.0 | 7–8 Hour MVP

DOCUENV

# Document Control

| Product | DocuEnv |
| --- | --- |
| Document | DocuEnv — Development Plan |
| Version | 1.0 — Initial MVP specification |
| Status | Working baseline; update as implementation decisions are verified |
| Scope | Client-side MVP; no backend, account system, or cloud persistence |

# 1. Development Principles

Build the smallest end-to-end product first. Prefer tested, pure functions over complex UI state. Do not add integrations, authentication, persistence, or dependencies without a clear MVP need.

Work in short verified steps. Do not claim a command passed unless it was actually run and its output inspected.

# 2. Proposed Stack

React + TypeScript + Vite for a static client-only app.

CSS modules or a minimal token-based styling approach.

Vitest for unit tests and Testing Library for selected UI tests.

Git and GitHub for version control; free static hosting for deployment after checking current terms.

Use the current stable compatible package versions at setup time; avoid hard-coding outdated version assumptions into documentation.

# 3. Repository Structure

src/app/ — application shell and orchestration.

src/components/ — input panels, findings table, type editor, output panel, privacy notice.

src/lib/env-parser.ts — supported .env parsing.

src/lib/compare.ts — key-set comparison and finding classification.

src/lib/infer-type.ts — advisory type inference.

src/lib/generate-zod.ts — Zod TypeScript output generation.

src/lib/generate-ci.ts — CI validation output generation.

src/types/ — shared domain types.

src/styles/ — design tokens and global styles.

tests/ or colocated *.test.ts files — unit tests.

docs/ — PRD, SRS, architecture, UI/UX, development plan, and rules.md.

# 4. Implementation Schedule

0:00–0:30 — Create repository, scaffold app, install dependencies, establish design tokens, and confirm dev server runs.

0:30–1:45 — Implement parser and parser tests: blank lines, comments, key=value, quoted values, duplicates, malformed lines, and empty values.

1:45–2:30 — Implement comparison engine and tests for missing, extra, and present keys.

2:30–3:15 — Implement advisory type inference and user override model.

3:15–4:15 — Implement Zod and CI output generators with snapshot/string assertions and example validation.

4:15–6:00 — Build primary UI: inputs, results, filters, type editor, output tabs, copy/download, sample/reset, privacy notice.

6:00–6:45 — Refine responsive layout, accessibility, empty/error states, and purposeful motion.

6:45–7:30 — Run all tests, lint/type checks, and production build; fix defects.

7:30–8:00 — Deploy, smoke-test production flows, update README/screenshots, and prepare release.

# 5. Development Sequence and Gates

Gate 1: development server starts and repository is initialized.

Gate 2: parser unit tests pass before UI depends on parser behavior.

Gate 3: comparison tests pass for missing/extra/present cases.

Gate 4: generated schema and CI output are inspected and tested against examples.

Gate 5: complete user flow works locally.

Gate 6: automated checks and production build pass.

Gate 7: deployed version is manually tested and privacy/network behavior verified.

# 6. Testing Strategy

Parser unit tests: blank lines, comments, spaces around equals, quoted values, escaped quotes where supported, empty values, duplicate keys, malformed lines, export-prefixed keys, and unsupported multiline syntax.

Comparison tests: empty files, identical files, missing keys, extra keys, duplicates, and stable ordering.

Inference tests: integer, boolean, URL, email, port, ordinary string, ambiguous strings, and boundary values.

Generator tests: valid syntax, correct required/optional behavior, escaping of key names, no inclusion of raw values, and predictable output.

UI tests: sample flow, parse warning display, filter changes, manual type override, copy/download fallback, reset behavior, and mobile layout smoke test.

Release checks: test command, lint/type check, production build, manual browser flow, and network inspection.

# 7. Git Workflow

Use small commits with meaningful messages, for example: feat: add env parser; test: cover duplicate keys; feat: add config diff; feat: generate zod schema; feat: add comparison workspace; fix: handle empty values.

Keep main branch buildable. Do not commit .env files, production secrets, or user-provided sample configuration containing credentials.

Add .env.example only with safe placeholder values. Use .gitignore to exclude local environment files.

# 8. Deployment and Release

Choose a free static host after checking current limits and account requirements.

Set build command and output directory correctly for the chosen framework.

Verify the public URL in a fresh browser session.

Test sample data, local file import, comparison, type override, schema generation, CI output, copy/download, reset, and mobile layout.

Inspect browser network requests to verify input text is not submitted.

Tag v1.0.0 only after the release gates pass; do not claim checks that were not performed.

# 9. Documentation and Portfolio

README should contain the problem, feature list, screenshots, quick start, supported syntax, privacy model, limitations, test/build commands, and deployment link.

Add LICENSE, CONTRIBUTING.md, SECURITY.md, and issue templates only where useful and accurate; avoid adding files solely for appearance.

Capture genuine screenshots from the deployed product.

LinkedIn post should explain the problem, the implementation, the privacy design, a real technical challenge, and the public demo/repository links.

# 10. Time-Scope Protection

If behind schedule, prioritize parsing, comparison, usable findings, and safe copyable output. Defer advanced inference categories, Web Workers, complex motion, saved projects, integrations, and PDF exports.

Do not compromise tests or privacy to add visual polish. Do not call the product production-ready until its reliability and security claims are substantiated.